## Study Organizer - Planning View
Study Organizer - Planning View (Business Plan)
Phase | Objective | Key Activities | Milestones | Responsible Team Member | Status (Progress %)
Research & Analysis | Gather market data and competitor insights | Conduct surveys, analyze industry reports, SWOT analysis | Finalized research report by Week 4 | Jane Doe (Research Lead) | 85%
Market Validation | Validate study demand and target audience needs | Focus groups, pilot testing, feedback collection | Metric: 90% positive response rate by Week 6 | John Smith (Product Manager) | 60%
Content Development | Create core study materials and curriculum | Outline modules, develop lesson plans, design assessments | All content completed by Week 10 | Alice Brown (Lead Instructor) | 45%
Pilot Testing | Run trial sessions with real participants | Organize 2 pilot cohorts, collect performance data | Pilot feedback analyzed by Week 13 | Michael Lee (Project Coordinator) | 20%
Refinement & Scaling | Improve materials based on feedback and plan rollout | Update curriculum, train instructors, build delivery system | All refinements approved by Week 16 | Sarah Wilson (Operations Director) | 0%
Summary Metrics
Total Planned Duration: |  |  | 16 weeks
Current Progress Average: |  |  | 48%
On Track: |  |  | Yes (with minor delays in pilot phase)