## Worksheet
Study Organizer - Team Use Business Plan Template
Team Member | Task/Responsibility | Deadline | Status | Progress (%) | Notes/Comments
John Doe | Research & Data Collection | 2024-10-15 | In Progress | 65% | Detailed analysis needed for final report.
Jane Smith | Market Analysis Report | 2024-10-18 | Not Started | 0% | To be reviewed by team lead.
Alex Johnson | Financial Projections | 2024-10-20 | In Progress | 45% | Requires updated cost estimates.
Sarah Brown | Marketing Strategy Outline | 2024-10-16 | In Progress | 70%
Michael Lee | Drafting Executive Summary | 2024-10-17 | In Progress | 55%
Total Project Completion: |  |  |  | 56% | Next Review: 2024-10-15
© 2024 Study Organizer - Team Use Business Plan Template ¦ Designed for collaborative academic planning