## Worksheet
Study Organizer - Gantt Chart (Planning View)
Task | Start Date | End Date | Duration (days) | Status | Progress
Week 1: Research & Planning | 2024-03-25 | 2024-03-31 | 7 | In Progress
Outline Study Plan | 2024-03-25 | 2024-03-26 | 1 | In Progress
Gather Study Materials | 2024-03-27 | 2024-03-31 | 5 | To Do
Week 2: Core Study Phase | 2024-04-01 | 2024-04-07 | 7 | To Do
Topic A - Fundamental Concepts | 2024-04-01 | 2024-04-03 | 3 | To Do
Topic B - Advanced Principles | 2024-04-04 | 2024-04-07 | 4 | To Do
Week 3: Practice & Review | 2024-04-08 | 2024-04-14 | 7 | To Do
Solve Practice Problems (Set 1) | 2024-04-08 | 2024-04-11 | 4 | To Do
Review and Correct Errors | 2024-04-12 | 2024-04-14 | 3 | To Do
Week 4: Final Review & Exam Prep | 2024-04-15 | 2024-04-21 | 7 | To Do
Full Mock Exam (Simulated) | 2024-04-15 | 2024-04-17 | 3 | To Do
Final Review & Weakness Focus | 2024-04-18 | 2024-04-21 | 4 | To Do
Final Exam Day | 2024-04-22 | 2024-04-22 | 1 | Milestone
Note: This Gantt chart is a visual planning tool. Update progress as tasks are completed.