## Worksheet
Task | Owner | Start Date | End Date | Progress (%) | Status
Project Kickoff | Team Lead | 2024-04-01 | 2024-04-03 | 100% | Complete
Research Phase | Researcher A | 2024-04-04 | 2024-04-15 | 85% | In Progress
Design Drafts | Designer B | 2024-04-16 | 2024-04-25 | 35% | In Progress
Development Sprint 1 | Dev Team | 2024-04-26 | 2024-05-10 | 15% | In Progress
Testing & QA | QA Engineer C | 2024-05-11 | 2024-05-25 | 5% | In Progress
Final Review & Submission | Team Lead | 2024-05-26 | 2024-05-31 | 0% | Pending