## Worksheet
Task | Start Date | End Date | Status | Assignee | Notes
Define Study Goals | 2023-10-01 | 2023-10-03 | To Do | John Doe | Outline main objectives and success criteria.
Research Topics | 2023-10-04 | 2023-10-10 | In Progress | Jane Smith | Gather relevant materials and references.
Create Study Schedule | 2023-10-11 | 2023-10-15 | In Progress | John Doe | Break down tasks by week and assign time slots.
Develop Study Materials | 2023-10-16 | 2023-10-25 | To Do | Jane Smith | Create flashcards, summaries, and practice questions.
Weekly Review Meeting | 2023-10-17 | 2023-10-17 | Completed | All Team Members | Assess progress and adjust plan if needed.
Practice Exams | 2023-10-26 | 2023-11-05 | To Do | All Team Members | Schedule full-length mock exams under timed conditions.
Final Review Session | 2023-11-06 | 2023-11-09 | To Do | John Doe | Focused revision on weak areas.
Project Completion & Feedback | 2023-11-10 | 2023-11-10 | To Do | All Team Members | Submit final report and collect feedback.