## Study Organizer - Project Plan
Study Organizer - Project Plan
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
T001 | Research Topic Overview | John Doe | 2024-04-01 | 2024-04-05 | In Progress | 75%
T002 | Create Outline and Structure | Jane Smith | 2024-04-06 | 2024-04-10 | Not Started | 0%
T003 | Write First Draft | Mike Johnson | 2024-04-11 | 2024-04-18 | Not Started | 0%
T004 | Citations and References Compilation | Sarah Brown | 2024-04-19 | 2024-04-23 | Not Started | 0%
T005 | Review and Edit Draft | All Team Members | 2024-04-24 | 2024-04-30 | Not Started | 0%
T006 | Final Proofreading and Submission Prep | Lisa White | 2024-05-01 | 2024-05-03 | Not Started | 0%
T999 | Final Submission | Professor Anderson | 2024-05-05 | 2024-05-05 | Pending Review | 10%
Total Tasks:7 ¦Completed:0 ¦In Progress:1 ¦Status Summary:On Track