## Study Organizer - Project Plan
Study Organizer - Project Plan (Extended Version)
# | Task / Activity | Start Date | Due Date | Priority | Progress | Assigned To | Notes / Resources
1 | Final Exam Preparation Phase I: Subject Foundation | 2024-03-01 | 2024-03-15 | High | 15% | Alice Johnson | Review syllabus, identify core topics per subject.
| 1.1 Review Biology Syllabus & Lecture Notes (Week 1) | 2024-03-01 | 2024-03-05 | Medium | 10% | Alice Johnson | Focus on cell biology, genetics, and evolution chapters.
| 1.2 Complete Chemistry Fundamentals Review (Week 2) | 2024-03-06 | 2024-03-15 | High | 8% | Alice Johnson | Practice balancing equations and stoichiometry.
2 | Milestone: Syllabus Review Complete - Phase I Complete | 2024-03-15 | 2024-03-15 | Critical | 100% | Alice Johnson | All core topics identified. Ready for Phase II.
3 | Phase II: Topic Deep Dive & Practice (Weeks 3–6) | 2024-03-16 | 2024-04-19 | High | 35% | Alice Johnson | Daily study sessions. Focus on weak areas.
| 3.1 Master Calculus Concepts (Week 3) | 2024-03-16 | 2024-03-29 | Medium | 40% | Alice Johnson | Work through textbook problems and online quizzes.
| 3.2 Practice Essay Writing (Week 5) | 2024-04-06 | 2024-04-19 | High | 30% | Alice Johnson | Use past paper prompts. Revise structure and argument.
4 | Milestone: Topic Deep Dive Complete - Phase II Complete | 2024-04-19 | 2024-04-19 | Critical | 100% | Alice Johnson | All topics covered. Ready for review and mock exams.
5 | Phase III: Mock Exams & Review (Weeks 7–8) | 2024-04-20 | 2024-05-17 | High | 65% | Alice Johnson | Simulate exam conditions. Analyze mistakes.
| 5.1 Complete 2 Full Mock Exams (Week 7) | 2024-04-20 | 2024-04-30 | High | 75% | Alice Johnson | Timed sessions. Self-grade using rubrics.
| 5.2 Target Weak Areas Based on Feedback (Week 8) | 2024-05-01 | 2024-05-17 | Medium | 60% | Alice Johnson | Revisit challenging topics. Practice specific problem types.
6 | Milestone: Final Prep Complete - Ready for Exam Day | 2024-05-17 | 2024-05-17 | Critical | 100% | Alice Johnson | All mock exams completed. Final review notes prepared.
Total Project Status |  | Overall Progress: 52% |  |  | 52%