## Worksheet
Study Organizer - Project Plan - Financial View
Task ID | Task Description | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Variance (USD)
T001 | Research & Literature Review | 2023-10-01 | 2023-10-15 | In Progress | $850.00 | $675.45 | $174.55 (Favorable)
T002 | Study Design & Methodology Planning | 2023-10-16 | 2023-10-31 | Planned | $950.00 | $45.75 | $904.25 (Favorable)
T003 | Data Collection & Fieldwork | 2023-11-01 | 2024-01-15 | Not Started | $6,500.00 | $0.00 | $6,500.00 (Favorable)
T011 | Software & Tool Licenses (Statistical Analysis) | 2023-11-15 | 2023-12-31 | In Progress | $450.00 | $398.67 | $51.33 (Favorable)
T022 | Participant Incentives & Compensation | 2024-01-01 | 2024-03-31 | Not Started | $5,895.00 | $76.59 | $5,818.41 (Favorable)
TOTALS: |  |  |  |  | $14,645.00 | $1,206.46 | $13,438.54 (Favorable)
Project Duration: October 1, 2023 – March 31, 2024 ¦ Prepared on: April 5, 2024