## Study Organizer - Project Plan
Study Organizer - Project Plan
Large Business Style ¦ Academic Project Management Template
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
T001 | Define Study Objectives and Scope | Dr. Amelia Wright | 2025-04-01 | 2025-04-05 | Complete | 100%
T002 | Research Literature Review | James Carter | 2025-04-06 | 2025-04-15 | In Progress | 75%
T003 | Develop Study Methodology | Sarah Thompson | 2025-04-16 | 2025-04-22 | In Progress | 60%
T004 | Data Collection Phase I | Robert Lee | 2025-04-23 | 2025-05-10 | Pending | 15%
T005 | Data Analysis and Interpretation | Linda Morgan | 2025-05-11 | 2025-06-15 | Pending | 0%
T006 | Draft Thesis Chapter I–III | Ethan Reed | 2025-06-16 | 2025-07-15 | Pending | 0%
T007 | Review and Feedback Session | Dr. Amelia Wright | 2025-07-16 | 2025-07-31 | Pending | 0%
T008 | Final Thesis Submission | All Team Members | 2025-08-01 | 2025-08-15 | Pending | 0%