## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Prioritization
#001 | Define Study Objectives | Jane Smith | 2025-04-01 | 2025-04-03 | Pending | High
#002 | Research Topic Literature Review | Mike Johnson | 2025-04-04 | 2025-04-11 | In Progress | High
#003 | Develop Study Framework | Sarah Lee | 2025-04-12 | 2025-04-18 | Pending
#004 | Collect Data from Sources | Daniel Brown | 2025-04-19 | 2025-04-30In Progress
#005 | Data Analysis & Validation | Emily Clark | 2025-05-01 | 2025-05-14Pending
#006 | Prepare Final Report Draft | Liam Wilson | 2025-05-15 | 2025-05-24Pending
#007 | Review and Feedback Session | Jane Smith, Mike Johnson | 2025-05-25 | 2025-05-31
#008 | Finalize & Submit Study Report | Sarah Lee, Emily Clark | 2025-06-01 | 2025-06-14
Pending
Note:This is a manager view of the Study Organizer Project Plan. Status and prioritization levels help track progress and focus attention on critical tasks.