## Study Organizer - Project Plan
Study Organizer - Project Plan (Office Use)
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | % Complete(Progress)
P1-01 | Define Study Objectives & Scope | Team Lead | 2024-04-01 | 2024-04-05 | In Progress | 75%
P1-02 | Identify Key Study Topics | Subject Expert | 2024-04-06 | 2024-04-15 | To Do | 15%
M1 | Study Plan Finalized | Project Manager | 2024-04-15 | 2024-04-15 | Completed✓ Complete | 100%
P2-01 | Collect Study Materials | Research Team | 2024-04-16 | 2024-05-05 | In Progress | 35%
P2-02 | Create Study Schedule | Coordinator | 2024-04-18 | 2024-04-30 | In Progress | 65%
M2 | Research Phase Complete | Project Manager | 2024-05-05 | 2024-05-05 | To Do⚠ Pending Review | 1%
P3-01 | Begin Daily Study Sessions | All Team Members | 2024-05-06 | 2024-06-15 | To Do⚠ Not Started Yet | 1%
P3-02 | Weekly Study Review Meetings | Team Lead | 2024-05-13 | 2024-06-15 | To Do⚠ Not Started Yet | 1%
M3 | Midpoint Study Assessment | Project Manager | 2024-06-01 | 2024-06-05 | To Do⚠ Not Started Yet | 1%
P4-01 | Compile Study Summary & Reports | Report Writer | 2024-06-16 | 2024-07-15 | To Do⚠ Not Started Yet | 1%
M4 | Final Study Report Submitted | Project Manager | 2024-07-15 | 2024-07-15 | To Do⚠ Not Started Yet | 1%
This template is designed for office use and may be adapted for academic or personal study planning. Version: 1.0