## Study Organizer - Project Plan
Study Organizer - Project Plan
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete
ST-001 | Research Topic Selection and Approval | Jane Doe | 2023-10-01 | 2023-10-15 | In Progress | 65%
ST-002 | Literature Review Draft (Part 1) | John Smith | 2023-10-16 | 2023-11-05 | In Progress | 45%
ST-003 | Data Collection Preparation | Alice Johnson | 2023-11-06 | 2023-11-25 | In Progress | 35%
ST-004 | Literature Review Draft (Part 2) | John Smith | 2023-11-26 | 2023-12-15 | Delayed | 80%
ST-005 | Data Collection Execution | Alice Johnson | 2023-11-26 | 2024-01-15 | In Progress | 75%
ST-006 | Data Analysis Phase I | Robert Brown | 2024-01-16 | 2024-01-31 | In Progress | 55%
ST-007 | Draft Final Report (Section 1) | Jane Doe | 2024-02-01 | 2024-02-15 | Not Started | 5%
ST-008 | Draft Final Report (Section 2) | John Smith | 2024-02-16 | 2024-03-15 | Not Started | 0%
ST-009 | Draft Final Report (Section 3) | Alice Johnson | 2024-03-16 | 2024-04-15 | Not Started | 0%
ST-010 | Final Review and Submission | Jane Doe, John Smith, Alice Johnson | 2024-04-16 | 2024-05-31 | Not Started | 0%