## Worksheet
Task | Responsible | Start Date | End Date | Status | Progress (%)
Define Project Scope | Project Manager | 2024-01-05 | 2024-01-10 | In Progress | 65%
Gather Requirements | Team Lead | 2024-01-11 | 2024-01-20 | In Progress | 45%
Design Study Framework | Research Analyst | 2024-01-21 | 2024-01-31 | In Progress | 30%
Develop Data Collection Tools | IT Specialist | 2024-02-01 | 2024-02-15 | In Progress | 15%
Recruit Study Participants | Coordinator | 2024-02-16 | 2024-03-15 | In Progress | 10%
Conduct Study Sessions | Research Team | 2024-03-16 | 2024-04-15 | Not Started | 0%
Analyze Results | Data Scientist | 2024-04-16 | 2024-05-15 | Not Started | 0%
Prepare Final Report | Project Manager | 2024-05-16 | 2024-06-15 | Not Started | 0%
Total Project Duration: |  |  |  |  | 2024-01-05 to 2024-06-15
Overall Progress: |  |  |  |  | 24%