## Worksheet
Study Organizer - Project Plan Summary View
Task ID | Task Name | Category | Status | Start Date | Due Date | Progress (%)
T001 | Research Topic & Literature Review | Research | In Progress | 2024-04-05 | 2024-05-15 | 68%
T002 | Outline Study Structure & Methodology | Planning | In Progress | 2024-04-15 | 2024-05-31 | 75%
T003 | Data Collection & Fieldwork | Execution | Pending | 2024-06-15 | 2024-07-31 | 5%
T004 | Data Analysis & Interpretation | Analysis | Pending | 2024-08-15 | 2024-09-30 | 1%
T005 | Write Final Report & Thesis Draft | Writing | Pending | 2024-10-15 | 2024-11-30 | 0%
T006 | Review & Finalize Presentation | Preparation | Pending | 2024-12-01 | 2024-12-15 | 0%
Total Tasks |  |  | 6
Overall Project Status
Completion Rate:62%