## Worksheet
Task | Assigned To | Status | Due Date | Priority | Description
Define project scope | Jane Smith | To Do | 2023-10-05 | High | Outline goals, deliverables, and constraints.
Create timeline | Mike Johnson | In Progress | 2023-10-10 | High | Develop Gantt chart with milestones.
Research materials | Alice Brown | In Progress | 2023-10-08 | Medium | Gather academic sources and references.
Design survey instrument | David Lee | To Do | 2023-10-12 | Medium | Create questions and validation criteria.
Review team contributions | Sarah Wilson | Completed | 2023-10-03 | Low | Weekly check-in and feedback session.
Preliminary report draft | Jane Smith | To Do | 2023-10-15 | High | Compile findings and initial analysis.