## Worksheet
Study Organizer - Project Template - Manager View
Project Overview
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Budget (USD) | % Complete
STUD-001 | Literature Review | Jane Smith | 2023-10-05 | 2023-11-15 | In Progress | $450.00 | 68%
STUD-002 | Research Design | Michael Brown | 2023-10-10 | 2023-11-30 | In Progress | $650.50 | 42%
STUD-003 | Data Collection | Sarah Johnson | 2023-11-01 | 2024-01-15 | Delayed | $980.75 | 9%
STUD-004 | Data Analysis | David Lee | 2023-11-15 | 2024-02-15 | Completed | $765.30 | 100%
STUD-005 | Report Writing | Lisa Wong | 2023-12-01 | 2024-03-15 | In Progress | $899.99 | 35%
STUD-006 | Final Review & Submission | Alex Turner | 2024-03-15 | 2024-03-31 | Completed | $150.00 | 100%
Total Project Summary |  |  |  |  | 6 Tasks | $4,971.54
Study Organizer - Project Template ¦ Manager View ¦ Exported on October 5, 2023