## Worksheet
Study Organizer - Project Timeline
Task | Start Date | End Date | Status | Assignee | Priority
Research & Outline Study Plan | 2023-10-01 | 2023-10-05 | In Progress | Alice Johnson | High
Collect Required Materials | 2023-10-06 | 2023-10-10 | In Progress | Robert Lee | High
Complete Module 1 - Foundations | 2023-10-11 | 2023-10-18 | Pending | Sarah Chen | Medium
Complete Module 2 - Intermediate Concepts | 2023-10-19 | 2023-10-25 | Pending | Liam Rodriguez | Medium
Complete Module 3 - Advanced Topics | 2023-10-26 | 2023-11-01 | Pending | Emma Thompson | High
Critical Review & Revision | 2023-11-02 | 2023-11-05 | Pending | Alice Johnson | High
Final Submission Preparation | 2023-11-06 | 2023-11-08 | Pending | All Team Members | High