## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Duration (Days) | Status | Priority | Dependencies | Notes
T001 | Define project scope and objectives | Project Manager | 2024-04-01 | 2024-04-05 | 5 | In Progress | High | - | Include all stakeholders in scope definition.
T002 | Create research outline and literature review | Researcher A | 2024-04-06 | 2024-04-15 | 10 | In Progress | Medium | T001 | Ensure sources are peer-reviewed and recent.
T003 | Conduct data collection (surveys & interviews) | Researcher B | 2024-04-16 | 2024-05-10 | 25 | Not Started | High | T002 | Schedule participants in advance.
T004 | Analyze collected data using statistical tools | Data Analyst | 2024-05-11 | 2024-05-31 | 21 | Not Started | Medium | T003 | Use SPSS and Excel for analysis.
T005 | Draft initial research report | Writer | 2024-06-01 | 2024-06-15 | 15 | Not Started | Low | T004 | Include charts and summary tables.
T006 | Review and revise report with team | Project Manager | 2024-06-16 | 2024-06-30 | 15 | Not Started | Medium | T005 | Schedule review meeting on June 20.
T007 | Finalize and submit research report | Project Manager | 2024-07-01 | 2024-07-15 | 15 | Not Started | Low | T006 | Submit in PDF and Word format.
Project Summary
Total Tasks: |  |  | 7 |  | Overall Progress: |  |  | 57%
Project Start Date: April 1, 2024 ¦ Project End Date: July 15, 2024