## Worksheet
Study Organizer
Project Timeline & Task Management Dashboard
Task ID | Task Description | Start Date | Due Date | Assigned To | Status
MT01 | Project Kickoff & Planning | 2023-10-05 | 2023-10-10 | Team Lead | Completed
MT02 | Research & Material Gathering Phase I | 2023-10-11 | 2023-10-25 | Alice Johnson | Completed
MT03 | First Draft Submission - Core Chapters | 2023-10-26 | 2023-11-15 | Brian Lee | In Progress
MT04 | Peer Review & Feedback Collection | 2023-11-16 | 2023-11-30 | Sarah Williams | In Progress
MT05 | Final Revision & Submission Prep | 2023-12-01 | 2023-12-15 | All Team Members | Delayed
MT06 | Final Submission & Presentation Prep | 2023-12-16 | 2023-12-31 | Maria Garcia | Delayed
T001 | Literature Review on Topic A | 2023-10-15 | 2023-10-25 | Alice Johnson | Completed
T002 | Outline Development - Chapter 1 & 2 | 2023-10-18 | 2023-10-31 | Brian Lee | In Progress
T003 | Data Collection & Analysis Methods | 2023-11-05 | 2023-11-14 | Sarah Williams | Completed
T004 | Draft Chapter 3 - Methodology Section | 2023-11-15 | 2023-11-28 | Brian Lee | In Progress
T005 | Review and Revise Chapters 1–3 Feedback | 2023-11-30 | 2023-12-14 | All Team Members | Delayed
T006 | Prepare Presentation Slides & Visuals | 2023-12-15 | 2023-12-31 | Maria Garcia | Delayed
Total Tasks: |  |  |  |  | 6