## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Progress (%) | Assigned To
T001 | Research Phase I: Literature Review | 2025-04-01 | 2025-04-15 | In Progress |  | Dr. Alice Johnson
T002 | Develop Study Framework | 2025-04-16 | 2025-04-30 | In Progress |  | Dr. Robert Chen
T003 | Participant Recruitment & Consent | 2025-05-01 | 2025-06-15 | Pending Start |  | Sarah Williams (Coordinator)
T004 | Data Collection & Monitoring | 2025-06-16 | 2025-08-31 | Pending Start |  | James Reed (Lead Researcher)
T005 | Data Analysis & Validation | 2025-09-01 | 2025-11-30 | Pending Start |  | Dr. Emily Zhang (Statistical Analyst)
T006 | Report Drafting & Review | 2025-12-01 | 2026-01-31 | Pending Start |  | Dr. Alice Johnson & Dr. Robert Chen
Final Project Submission (Milestone)
T007 | Final Report Submission & Presentation | 2026-02-15 | 2026-02-15 | Pending Start |  | Dr. Emily Zhang (Lead)
This timeline is a high-level overview for project management. Actual progress may vary. Last updated on: April 5, 2025