## Worksheet
Study Organizer - Project Timeline (Multi-Page)
Task ID | Task Description | Start Date | End Date | Status | Priority | Assigned To(Study Group)
T001 | Define Study Goals & Outline Topics | 2024-04-05 | 2024-04-15 | Completed ✅ | High 🟩 | Alice, Bob, Chloe(Team A)
T002 | Research Key Concepts & Gather Materials | 2024-04-16 | 2024-05-15 | In Progress 🟡 | High 🟩 | Dave, Emma (Team B)
T003 | Create Study Schedule & Weekly Plan | 2024-04-18 | 2024-05-15 | In Progress 🟡 | High 🟩 | Alice, Chloe (Team A)
T004 | Organize Flashcards & Summary Sheets | 2024-05-16 | 2024-06-15 | Not Started 🔴 | Medium 🟨 | Brian, Dave (Team C)
T005 | Weekly Review & Progress Tracking | 2024-05-17 | 2024-06-30 | Not Started 🔴 | Medium 🟨 | All Team Leads (Shared)
T006 | Practice Exam Simulations & Feedback Loop | 2024-06-15 | 2024-07-15 | Not Started 🔴 | High 🟩 | All Members (Team A/B/C)
T007 | Final Review & Confidence Assessment | 2024-07-16 | 2024-07-31 | Not Started 🔴 | High 🟩 | All Members (Team A/B/C)
T008 | Submit Final Project Report & Presentation Prep | 2024-07-15 | 2024-07-31 | Not Started 🔴 | High 🟩 | Alice, Emma (Team A/B)
T009 | Post-Study Evaluation & Feedback Collection | 2024-08-01 | 2024-08-15 | Not Started 🔴 | Low 🟥 | All Members (Shared)
T010 | Celebration & Reflection Session(Post-Course)(Optional Event) | 2024-08-16 | 2024-08-17 | Not Started 🔴 | N/A (🎉) | All Members (Team A/B/C)
Project Summary & Key Metrics
Total Tasks: |  |  | 10
Completed: |  |  | 1 (10%)
In Progress: |  |  | 2 (20%)
Not Started: |  |  | 7 (70%)
Critical Path Tasks: |  |  | T002, T003, T010 (High Priority)
Notes & Comments
• Weekly check-ins scheduled every Friday at 4 PM. • Use shared Google Drive folder for document access and updates. • Deadline extensions require written approval from Team Lead. • Focus on active recall and spaced repetition techniques during study sessions. • Encourage peer teaching between team members to reinforce learning.