## Worksheet
Study Organizer - Project Timeline
Task ID | Task Name | Start Date | End Date | Status | Priority
T001 | Research Topic Selection | 2024-04-01 | 2024-04-05 | Completed | High
T002 | Literature Review Draft | 2024-04-06 | 2024-04-15 | In Progress | High
T003 | Data Collection Plan | 2024-04-16 | 2024-04-25 | Pending | Medium
T004 | Survey Design & Validation | 2024-04-26 | 2024-05-10 | Pending | High
T005 | Data Analysis & Interpretation | 2024-05-11 | 2024-05-31 | Pending | High
T006 | Initial Draft Completion | 2024-06-01 | 2024-06-15 | Pending | Medium
T007 | Review & Feedback Incorporation | 2024-06-16 | 2024-06-30 | Pending | High
T008 | Final Submission Preparation | 2024-07-01 | 2024-07-15 | Pending | High