## Worksheet
Study Organizer - Project Timeline
Task ID | Task Description | Start Date | Due Date | Status | Priority(1-5)
T001 | Research Topic & Background Literature | 2024-04-01 | 2024-04-15 | In Progress | 5
T002 | Outline Study Structure & Methodology(e.g., survey design, data collection) | 2024-04-16 | 2024-04-25 | Pending | 5
T003 | Conduct Initial Survey / Data Collection Phase 1(Sample: 100 participants) | 2024-04-26 | 2024-05-15 | Pending | 4
T004 | Data Analysis & Preliminary Findings Review(Using statistical tools) | 2024-05-16 | 2024-05-31 | Pending | 5
T005 | Write Draft Section: Introduction & Methods(First 2 chapters) | 2024-06-01 | 2024-06-15 | Pending | 5
T006 | Peer Review & Feedback Integration (Internal)(From mentor/team) | 2024-06-16 | 2024-06-30 | Pending | 4
T007 | Finalize Research Paper Draft & Formatting Compliance (APA, IEEE, or institutional standard) | 2024-07-01 | 2024-07-15 | Pending | 5
T008 | Submit Final Version for Academic Review & Approval (Department submission) | 2024-07-16 | 2024-07-31 | Pending | 5
Project Duration:April 1, 2024 – July 31, 2024
Total Tasks:8 ¦Status Summary:In Progress (1), Pending (7)