## Worksheet
Study Organizer - Project Timeline Report
Academic Project Schedule ¦ Reporting Period: January 2025 - June 2025
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Budget (USD)
TASK-001 | Literature Review & Research Phase | Jan 05, 2025 | Feb 18, 2025 | In Progress | Alice Johnson | $475.00
TASK-002 | Develop Research Framework & Hypothesis | Feb 19, 2025 | Mar 15, 2025 | In Progress | Robert Lee | $380.00
TASK-003 | Data Collection & Survey Deployment | Mar 16, 2025 | Apr 29, 2025 | Pending | Sophia Martinez | $850.00
TASK-004 | Data Analysis & Interpretation | May 01, 2025 | May 31, 2025 | Pending | Daniel Kim | $760.00
TASK-005 | Write Final Report & Prepare Presentation | Jun 01, 2025 | Jun 14, 2025 | Pending | Lisa Chen | $690.00
Total Project Cost: | [5 empty] | $3,155.00
Note:This timeline is subject to change based on feedback and milestone completion. All team members are encouraged to update task statuses bi-weekly.