## Worksheet
Study Organizer - Project Timeline (Summary View)
Task ID | Task Description | Start Date | End Date | Status | Assigned To
TASK-001 | Research Topic Background | 2023-10-01 | 2023-10-05 | Completed | Alice Johnson
TASK-002 | Outline Study Structure | 2023-10-06 | 2023-10-10 | In Progress | Bob Smith
TASK-003 | Collect Academic Sources | 2023-10-11 | 2023-10-18 | In Progress | Carol White
TASK-004 | Write Introduction Section | 2023-10-19 | 2023-10-25 | Pending | Alice Johnson
TASK-005 | Develop Hypothesis & Research Questions | 2023-10-26 | 2023-11-01 | Pending | Bob Smith
TASK-006 | Analyze Preliminary Data | 2023-11-02 | 2023-11-08 | Pending | Carol White
TASK-007 | Finalize Study Design | 2023-11-09 | 2023-11-15 | Pending | Alice Johnson
Total Tasks: |  |  |  |  | 8