## Worksheet
Study Organizer - Project Timeline (Team Use)
Collaborative project planning & tracking for academic success
Task | Owner | Start Date | Due Date | Status | Progress (%)
Research Topic Selection | Alice Johnson | 2025-04-01 | 2025-04-05 | In Progress | 65%
Literature Review Draft | Bob Smith | 2025-04-06 | 2025-04-15 | In Progress | 40%
Methodology Design | Claire Brown | 2025-04-16 | 2025-04-20 | Not Started | 0%
Data Collection Phase I | David Lee | 2025-04-21 | 2025-04-30 | Not Started | 0%
Analysis & Interpretation | Elena Martinez | 2025-05-01 | 2025-05-10 | Not Started | 0%
Draft Report Writing | Fiona Taylor | 2025-05-11 | 2025-05-25 | Not Started | 0%
Peer Review & Feedback | Team (Shared) | 2025-05-26 | 2025-06-01 | Not Started | 0%
Final Submission Preparation | All Members | 2025-06-02 | 2025-06-10 | Not Started | 0%
Submission & Presentation | All Members | 2025-06-11 | 2025-06-15 | Not Started | 0%
Post-Project Reflection | All Members | 2025-06-16 | 2025-06-18 | Not Started | 0%
Updated on April 1, 2025 ¦ Version v1.0