## Worksheet
Study Organizer - Project Tracker
Multi-Page Template for Academic and Research Projects
OverviewTasks & ScheduleProgress TrackingResources & Materials
Project Overview
Project Name | Advanced Research in Machine Learning Applications
Student/Researcher | Alice Johnson
Course/Department | CSE 450 - Advanced AI Research
Start Date | 2023-10-01
End Date | 2024-05-31
Status | In Progress
Progress Rate | 68%
Project Goals & Objectives
Develop a novel algorithm for anomaly detection in time-series data
Implement and test model performance on real-world datasets
Write comprehensive research paper for publication in IEEE conference
Create detailed technical documentation and presentation materials
Key Milestones
Milestone | Deadline | Status
Literature Review Completion | 2023-11-30 | Completed
Algorithm Design Phase | 2024-01-15 | In Progress
Data Collection & Preprocessing | 2024-03-10 | Pending
Model Testing & Validation | 2024-05-15 | Pending
Final Report Submission | 2024-05-31 | Pending
Task List & Weekly Schedule
Task ID | Task Description | Priority | Status | Assigned To | Due Date
TASK-001 | Literature Review on Time-Series Anomaly Detection | High | Completed | Alice Johnson | 2023-11-30
TASK-002 | Design Architecture for New Anomaly Detection Algorithm | High | In Progress | Alice Johnson | 2024-01-15
TASK-003 | Collect Public Datasets for Testing (Kaggle, UCI) | Medium | Pending | Alice Johnson | 2024-03-10
TASK-004 | Implement Algorithm in Python using PyTorch | High | Pending | Alice Johnson | 2024-04-15
TASK-005 | Test Model Performance on Multiple Datasets | High | Pending | Alice Johnson | 2024-05-15
TASK-006 | Write Research Paper and Prepare Presentation | Medium | Pending | Alice Johnson | 2024-05-31
TASK-007 | Review by Advisor and Incorporate Feedback | High | Pending | Alice Johnson, Dr. Smith | 2024-05-10
TASK-008 | Final Submission & Defense Preparation | High | Pending | Alice Johnson | 2024-05-31
TASK-009 | Archive Code and Documentation | Low | Pending | Alice Johnson | 2024-06-05
TASK-010 | Plan Next Research Phase (If Applicable) | Medium | Pending | Alice Johnson | 2024-06-15
Weekly Study Schedule (Sample Week)
Day | Time Slot | Activity Type | Description
Monday | 09:00 - 11:00 AM | Lecture & Discussion | Weekly research group meeting with advisor (virtual)
Tuesday | 02:00 - 4:00 PM | Research & Coding | Implement algorithm modules using PyTorch framework
Wednesday | 10:00 - 12:00 PM | Study Session | Review academic papers on deep learning architectures
Thursday | 14:00 - 16:00 PM | Lab Work & Testing | Run experiments on dataset and analyze results
Friday | 09:00 - 11:00 AM | Writing & Documentation | Draft section of research paper on methodology
Saturday | 11:00 - 13:00 PM | Review & Planning | Weekly review of progress and task planning for next week
Progress & Performance Metrics
Metric | Target Value | Current Value | Status
Overall Task Completion Rate | 100% | 68% | On Track
Milestone Achievement Rate | 100% | 60% | On Track
Research Paper Draft Progress | 100% | 35% | On Track
Code Module Completion | 100% | 45% | On Track
Experiment Test Cases Completed | 100% | 55% | On Track
Average Study Hours/Week | 20 hours | 16 hours | Slight Delay
Progress Timeline Graph (Text Representation)
Progress Over Time (Percentage) 100% ¦ * 80% ¦ * 60% ¦ * 40% ¦ * 20% ¦ * 0% +------------------- Oct Nov Dec Jan Feb Mar Apr May Jun Month
Note:This visual represents approximate progress; actual values are shown in the table above.