## Worksheet
Month | Task Category | Task Description | Planned Start Date | Planned End Date | Resource Allocation | Estimated Cost (USD) | Budgeted % of Annual Total | Status
January | Project Initiation | Feasibility Study & Stakeholder Alignment | 2024-01-01 | 2024-01-31 | Project Manager, Analysts (3) | 15,000 | 4.5% | On Track
February | Resource Planning | Team Assignment & Tool Setup | 2024-02-01 | 2024-02-28 | HR, Operations Lead | 10,500 | 3.1% | On Track
March | Design & Development | System Architecture Finalization | 2024-03-01 | 2024-03-31 | Engineers (6), Architects | 50,000 | 15.0% | On Track
April | Development & Testing | Alpha Release & Unit Testing | 2024-04-01 | 2024-04-30 | Developers (8), QA Team | 75,000 | 22.5% | On Track
May | User Acceptance Testing | Client Feedback & Final Adjustments | 2024-05-01 | 2024-05-31 | Clients, QA Team, Project Manager | 35,000 | 10.5% | On Track
June | Deployment & Go-Live | System Launch to Production Environment | 2024-06-01 | 2024-06-30 | IT Ops, Support Team | 45,000 | 13.5% | On Track
July | Post-Go-Live Review | Performance Monitoring & Reporting | 2024-07-01 | 2024-07-31 | Analysts, Support Team | 18,000 | 5.4% | On Track
August | Training & Documentation | Staff Onboarding & Knowledge Transfer | 2024-08-01 | 2024-08-31 | HR, Training Officers | 12,000 | 3.6% | On Track
September | Performance Optimization | System Scalability & Security Audit | 2024-09-01 | 2024-09-30 | Security Team, DevOps | 38,000 | 11.4% | On Track
October | Review & Planning for Year 2 | Annual Performance Analysis & Future Roadmap | 2024-10-01 | 2024-10-31 | Project Manager, Finance Team | 8,500 | 2.5% | On Track
November | Compliance & Audit | Regulatory Compliance Checks | 2024-11-01 | 2024-11-30 | Legal, Compliance Officer | 9,500 | 2.8% | On Track
December | Year-End Reporting | Financial Summary & Budget Closure | 2024-12-01 | 2024-12-31 | Finance Team, Leadership | 7,500 | 2.3% | On Track
Total Annual Budget (USD) | [6 empty] | 318,000 | 100.0%