## Worksheet
Month | Task Category | Task Description | Responsible Person | Start Date | End Date | Estimated Hours | Budget Allocation ($) | Status
January | Project Planning | Finalize annual project roadmap and timelines | Sarah Chen | 01/01/2024 | 01/31/2024 | 8 | 800 | On Track
February | Team Training | Conduct onboarding and skill-building sessions | James Wilson | 02/05/2024 | 02/15/2024 | 16 | 1,600.00 | Scheduled
March | Market Analysis | Review quarterly market trends and customer behavior | Lena Park | 03/01/2024 | 03/28/2024 | 12 | 1,200.00 | In Progress
April | Product Development | Prototype testing and user feedback collection | Marcus Reed | 04/03/2024 | 04/30/2024 | 24 | 2,400.00 | Pending Approval
May | Financial Review | Conduct budget variance analysis and forecasting | Amina Torres | 05/01/2024 | 05/31/2024 | 10 | 1,000.00 | On Track
June | Customer Feedback Loop | Analyze customer satisfaction reports and act on findings | David Kim | 06/01/2024 | 06/30/2024 | 18 | 1,800.00 | Scheduled
July | Quarterly Reporting | Prepare and present results to executive leadership | Emily Clark | 07/01/2024 | 07/31/2024 | 6 | 600 | Planned
August | Process Optimization | Review workflows and propose automation improvements | Thomas Brown | 08/01/2024 | 08/31/2024 | 14 | 1,400.00 | Pending Review
September | New Initiative Launch | Roll out new product feature to selected markets | Sophia Lee | 09/01/2024 | 09/30/2024 | 28 | 2,800.00 | In Progress
October | Performance Audit | Evaluate team performance and key KPIs | Nathan Foster | 10/01/2024 | 10/31/2024 | 16 | 1,600.00 | Scheduled
November | Year-End Planning | Begin preparation for next fiscal year | Olivia Martinez | 11/01/2024 | 11/30/2024 | 8 | 800 | On Track
December | Review & Closeout | Finalize all reports, conduct team evaluation, and archive data | Robert Hill | 12/01/2024 | 12/31/2024 | 6 | 600 | Pending Start