## Worksheet
Quarter | Task Category | Planned Start Date | Planned End Date | Resource Allocation | Budget (USD) | Status
Q1 (Jan–Mar) | Project Initiation & Planning | 2024-01-01 | 2024-03-31 | Project Manager, 2 Analysts | $50,000 | In Progress
Q2 (Apr–Jun) | Development & Design Phase | 2024-04-01 | 2024-06-30 | Development Team, UI/UX Designer | $120,000 | On Track
Q3 (Jul–Sep) | Testing & Quality Assurance | 2024-07-01 | 2024-09-30 | QA Engineers, Test Leads | $65,000 | Pending Review
Q4 (Oct–Dec) | Deployment & Post-Implementation Review | 2024-10-01 | 2024-12-31 | Operations Team, Client Support | $75,000 | Pending Final Approval