## Worksheet
Month | Task Name | Responsible Person | Start Date | End Date | Estimated Hours | Status | Priority
January | Product Roadmap Finalization | Alex Morgan | 01/05/2024 | 01/31/2024 | 40 | In Progress | High
February | UI/UX Design Review | Jamie Lee | 02/01/2024 | 02/15/2024 | 30 | Not Started | High
March | Backend Development Phase | Sam Patel | 03/05/2024 | 03/30/2024 | 60 | Planned | Critical
April | Alpha Testing Initiation | Taylor Reed | 04/01/2024 | 04/30/2024 | 50 | Not Started | High
May | User Feedback Collection | Morgan Chen | 05/01/2024 | 05/31/2024 | 35 | In Progress | Medium
June | Beta Release Preparation | Lena Kim | 06/05/2024 | 06/30/2024 | 45 | Not Started | High
July | Performance Optimization | Jake Ruiz | 07/01/2024 | 07/31/2024 | 55 | Planned | High
August | Security Audit | Elena Torres | 08/01/2024 | 08/31/2024 | 40 | Not Started | Critical
September | Marketing Campaign Launch | Nathan Wright | 09/05/2024 | 09/30/2024 | 60 | Planned | High
October | Team Training & Onboarding | Sophia Liu | 10/01/2024 | 10/31/2024 | 50 | Not Started | Medium
November | Quarterly Review & Planning | Alex Morgan | 11/05/2024 | 11/30/2024 | 45 | In Progress | High
December | Year-End Reporting & Strategy | Jamie Lee | 12/01/2024 | 12/31/2024 | 60 | Planned | Critical