## Worksheet
Month | Task Name | Responsible Person | Start Date | End Date | Status | Progress (%) | Budget Allocation ($) | Actual Spend ($) | Variance ($)
January | Project Kickoff Meeting | John Doe | 2024-01-01 | 2024-01-05 | Completed | 100% | 500 | 480 | 20
February | Market Research Phase | Jane Smith | 2024-02-01 | 2024-02-15 | In Progress | 65% | 3,000 | 2,200 | 800
March | Prototype Development | Mike Johnson | 2024-03-01 | 2024-03-31 | Delayed | 40% | 8,500 | 6,200 | +2,300
April | Testing & QA Review | Lisa Chen | 2024-04-01 | 2024-04-30 | Completed | 100% | 7,200 | 7,150 | 50
May | Training Session Setup | Robert Kim | 2024-05-01 | 2024-05-15 | Planned | 0% | 1,800 | 0 | -
June | Final Client Review | Sarah Patel | 2024-06-01 | 2024-06-30 | Completed | 100% | 4,500 | 4,480 | 20
Total Budget: |  |  |  | $21,700 | Total Actual Spend: |  |  | $19,930