## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Responsible Department | Resource Allocation | Dependencies
TS-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-03 | High | Completed | Project Management | 1 Full-Time | None
TS-002 | Requirement Analysis | John Doe | 2024-04-04 | 2024-04-15 | High | In Progress | Product Development | 2 Full-Time | TS-001
TS-003 | UI/UX Design Finalization | Alice Johnson | 2024-04-16 | 2024-05-01 | Medium | Pending | Design Team | 1 Part-Time + 1 Freelancer | TS-002
TS-004 | Backend Development Phase 1 | Robert Lee | 2024-05-02 | 2024-06-15 | High | Planned | Engineering Team | 3 Full-Time | TS-003, TS-005
TS-005 | Testing & Quality Assurance | Samantha Park | 2024-06-16 | 2024-07-30 | High | Pending | QA Department | 2 Full-Time + 1 External Vendor | TS-004