## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date th> | Status | Priority | Resource Allocation | Dependency | Progress (%)
T-001 | Project Planning Phase | John Doe | 2024-03-15 | 2024-03-31 | Active | High | Full Team | None | 100%
T-002 | Requirement Gathering | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | Medium | Requirements Team | T-001 | 65%
T-003 | Design Phase | Mike Johnson | 2024-04-16 | 2024-05-10 | Planned | High | Design Team | T-002 | 0%
T-004 | Development & Testing | Sarah Lee | 2024-05-11 | 2024-07-30 | Pending | Critical | Engineering Team | T-003 | 0%