## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resources Required
T001 | Project Kickoff Meeting | John Smith | 2024-03-15 | 2024-03-16 | Completed | Low | Team Lead, Meeting Room A
T002 | Requirements Gathering | Lisa Chen | 2024-03-17 | 2024-03-25 | In Progress | Medium | Stakeholders, Research Tools
T003 | UI/UX Design Phase | Alex Rivera | 2024-03-26 | 2024-04-10 | Planned | High | Design Team, Sketching Tools
T004 | Development Sprint 1 | Mike Taylor | 2024-04-11 | 2024-04-25 | Pending Approval | High | Backend Team, Servers, APIs
Task Scheduling - Client View ¦ Balance Sheet Style