## Worksheet
Task ID | Task Name | Assigned To | Priority | Start Date | Due Date | Status | Progress (%) | Estimated Duration (Days)
TSK-001 | Project Planning Phase | John Doe | High | 2024-03-15 | 2024-03-31 | In Progress | 65% | 17
TSK-002 | Requirement Gathering | Jane Smith | Medium | 2024-03-18 | 2024-04-05 | Not Started | 0% | 10
TSK-003 | UI/UX Design Finalization | Alex Brown | High | 2024-04-01 | 2024-04-15 | Scheduled | 0% | 15
TSK-004 | Backend Development | Mike Johnson | Critical | 2024-04-16 | 2024-05-10 | Not Started | 0% | 35
TSK-005 | Testing & QA | Sarah Lee | Medium | 2024-05-11 | 2024-06-01 | Planned | 0% | 20