## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resource Allocation
T001 | Project Planning Phase | Alice Johnson | 2024-03-15 | 2024-03-25 | In Progress | High | Team A, 3 members
T002 | UI/UX Design Finalization | Bob Smith | 2024-03-20 | 2024-04-10 | Pending | Medium | Design Team, 2 members
T003 | Backend Development | Charlie Lee | 2024-04-01 | 2024-05-15 | Planned | High | Engineering Team, 5 members
T004 | Testing & QA Cycle | Diana Patel | 2024-05-16 | 2024-06-10 | Not Started | High | QA Team, 3 members
T005 | Deployment & Launch | Evan Brown | 2024-06-11 | 2024-06-15 | Scheduled | Critical | Operations Team, 2 members