## Worksheet
Month | Task Name | Assigned To | Start Date | End Date | Status | Priority | Responsible Team
January | Project Planning | John Doe | 2024-01-01 | 2024-01-31 | Completed | High | Product Team
January | User Requirement Review | Jane Smith | 2024-01-15 | 2024-01-25 | In Progress | Medium | Product Team
January | Design Approval | Alex Chen | 2024-01-20 | 2024-01-30 | Completed | High | Design Team
February | Development Kickoff | Michael Lee | 2024-02-01 | 2024-02-15 | Scheduled | High | Engineering Team
February | QA Testing Phase | Sarah Kim | 2024-02-16 | 2024-03-01 | Pending | Medium | QA Team