## Worksheet
Page | Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resource Allocation
1 | TSK-001 | Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-03 | In Progress | High | Team A, 1 FTE
1 | TSK-002 | Requirements Gathering | Jane Smith | 2024-04-04 | 2024-04-15 | Scheduled | High | Team B, 2 FTE
1 | TSK-003 | UI/UX Design Phase | Alex Chen | 2024-04-16 | 2024-05-10 | Planned | Medium | Designer Team, 3 FTE
2 | TSK-004 | Backend Development Start | Mike Brown | 2024-05-11 | 2024-07-30 | Scheduled | High | Engineers, 5 FTE
2 | TSK-005 | API Integration Testing | Sarah Lee | 2024-08-01 | 2024-08-15 | Pending | Medium | QA Team, 2 FTE
2 | TSK-006 | User Acceptance Testing (UAT) | David Kim | 2024-08-16 | 2024-09-05 | Not Started | High | Client + QA, 3 FTE
Total Tasks Across Pages: 6 | [7 empty] | —