## Worksheet
Task ID | Task Name | Owner | Start Date | End Date th> | Duration (Days) | Status | Priority | Resources Required
T-001 | Project Initiation | John Doe | 2024-03-01 | 2024-03-15 | 15 | In Progress | High | Project Manager, Team Lead
T-002 | Requirements Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | 35 | Planned | High | Business Analyst, Stakeholders
T-003 | Design Phase | Mike Johnson | 2024-04-11 | 2024-05-05 | 35 | Not Started | Medium | UI/UX Designer, Developer
T-004 | Development Phase | Sarah Lee | 2024-05-06 | 2024-07-15 | 70 | Not Started | High | Software Developers, QA Engineers
T-005 | Testing & Validation | David Brown | 2024-07-16 | 2024-08-10 | 35 | Planned | High | QA Team, Test Managers
Total Tasks |  |  |  | 5