## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Resource Required
T001 | Project Planning Phase | John Doe | 2024-04-01 | 2024-04-15 | In Progress | High | Project Manager, Team Lead
T002 | Design Review Meeting | Jane Smith | 2024-04-16 | 2024-04-17 | Planned | Medium | Design Team, UX Lead
T003 | Development Phase - Backend | Mike Johnson | 2024-04-18 | 2024-05-10 | Not Started | High | Backend Engineer x3
T004 | QA Testing Cycle | Sarah Lee | 2024-05-11 | 2024-05-30 | Scheduled | Medium | QA Team, Automation Tools
T005 | Client Presentation | David Kim | 2024-06-01 | 2024-06-05 | Not Started | High | Marketing & Client Relations
Total Tasks Scheduled: 5