## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Responsible Team
T-001 | Project Planning Phase | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | High | Project Management Team
T-002 | Design Finalization | John Smith | 2024-04-05 | 2024-04-20 | Planned | Medium | Design Team
T-003 | Development Sprint | Alex Johnson | 2024-04-16 | 2024-05-05 | In Progress | High | Engineering Team
T-004 | QA Testing Phase | Sarah Lee | 2024-05-06 | 2024-05-20 | Not Started | Medium | Quality Assurance Team
T-005 | Final Review & Deployment | Michael Brown | 2024-05-21 | 2024-05-30 | Scheduled | Low | Operations Team