## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority | Status | Resources Required | Dependencies
T001 | Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-03 | High | In Progress | 1 Designer, 1 Manager | None
T002 | Requirement Gathering | Product Analyst | 2024-04-04 | 2024-04-15 | High | Planned | 3 Analysts, 1 Stakeholder | T001
T003 | UI/UX Design Phase | UX Designer | 2024-04-16 | 2024-05-01 | Medium | Not Started | 1 Designer, 1 Researcher | T002
T004 | Development Sprint 1 | Engineering Team | 2024-05-02 | 2024-05-15 | High | Scheduled | 5 Developers, 1 QA Lead | T003
T005 | Testing & Bug Fixing | QA Team | 2024-05-16 | 2024-05-31 | Medium | Scheduled | 4 QA Engineers, 1 Tester | T004