## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Progress % | Estimated Hours | Actual Hours
T-001 | Project Planning Phase | Jane Smith | 2024-03-15 | 2024-03-30 | In Progress | High | 65% | 16 | 12
T-002 | Design Review Meeting | John Doe | 2024-03-20 | 2024-03-25 | Completed | Medium | 100% | 8 | 8
T-003 | Backend Development Setup | Alice Brown | 2024-03-25 | 2024-04-10 | Pending | High | 0% | 24 | 0
T-004 | User Testing Phase | Mike Wilson | 2024-04-15 | 2024-05-01 | Not Started | Medium | 0% | 32 | 0