## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Priority Level | Status | Estimated Hours | Actual Hours | Progress (%)
TS-001 | Design Project Proposal | Jane Smith | 2024-04-01 | 2024-04-15 | High | In Progress | 16 | 12 | 75%
TS-002 | Develop API Endpoints | Alex Chen | 2024-04-10 | 2024-05-05 | Medium | Not Started | 24 | 0 | 0%
TS-003 | User Testing & Feedback | Sara Kim | 2024-05-10 | 2024-05-30 | Low | Planned | 18 | 0 | 0%
TS-004 | Finalize Documentation | Michael Lee | 2024-06-01 | 2024-06-15 | High | Not Started | 10 | 0 | 0%