## Worksheet
Task ID | Task Name | Assigned To | Due Date | Status | Priority | Start Date | Estimated Hours | Actual Hours | Progress (%)
T001 | Design Project Proposal | Jane Smith | 2024-04-15 | Completed | Medium | 2024-03-10 | 8 | 7.5 | 93.75%
T002 | Develop API Integration | Mike Johnson | 2024-05-30 | In Progress | High | 2024-04-05 | 16 | 10.2 | 63.75%
T003 | Conduct User Testing | Sarah Lee | 2024-06-10 | Pending | Medium | 2024-05-15 | 12 | 0 | 0%
T004 | Finalize Documentation | David Kim | 2024-06-25 | Completed | Low | 2024-05-30 | 6 | 5.8 | 96.67%