## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Estimated Hours | Actual Hours | Progress (%) | Notes
TSK-001 | Project Kickoff Meeting | John Doe | 2024-04-05 | High | Completed | 4 | 4 | 100%
TSK-002 | Design Phase Review | Jane Smith | 2024-04-10 | Medium | In Progress | 8 | 3.5 | 43.75% | Need to finalize wireframes by Thursday.
TSK-003 | Backend Development | Alex Johnson | 2024-04-15 | High | Pending | 16 | 0 | 0% | Start on Monday; requires API documentation.
TSK-004 | User Testing Sessions | Maria Lopez | 2024-04-25 | Medium | Not Started | 12 | 0 | 0% | Schedule with QA team; feedback needed.