## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Budgeted Cost | Actual Cost | Dependencies | Notes
TSK-001 | Project Kickoff Meeting | Jane Smith | 2024-04-01 | 2024-04-01 | Completed | Low | 2.5 | 2.5 | $150.00 | $150.00 | - | Confirmed all stakeholders and initial timelines.
TSK-002 | Requirements Gathering | John Doe | 2024-04-02 | 2024-04-15 | In Progress | Medium | 16 | 8.5 | $800.00 | $425.00 | TSK-001 | First draft reviewed by PM.
TSK-003 | UI/UX Design Finalization | Sarah Lee | 2024-04-16 | 2024-05-10 | Planned | High | 32 | 0 | $1600.00 | $0.00 | TSK-002 | Final designs to be approved by client.
TSK-004 | Development Phase - Backend | Mike Chen | 2024-05-11 | 2024-06-30 | Not Started | High | 80 | 0 | $4000.00 | $0.00 | TSK-003 | Framework setup and API integration.
TSK-005 | Testing & QA Validation | Lisa Wang | 2024-07-01 | 2024-07-31 | Scheduled | Medium | 35 | 0 | $1750.00 | $0.00 | TSK-004 | Automated tests to be implemented.
Total Tasks | [5 empty] | 5 | 100 | 32.5 | $8300.00 | $1975.00 | -