## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Priority | Estimated Hours | Actual Hours | Notes
TSK-001 | Design project timeline and schedule | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress | High | 8 | 5 | Initial draft review scheduled for April 5.
TSK-002 | <Conduct stakeholder meetings | John Doe | 2024-04-10 | 2024-04-18 | Completed | Medium | 6 | 6 | All stakeholders confirmed and feedback collected.
TSK-003 | Develop task automation scripts | Lisa Chen | 2024-04-20 | 2024-05-10 | Pending | High | 12 | 0 | Script development in progress; testing to follow.
TSK-004 | Review project budget allocation | Mark Wilson | 2024-04-12 | 2024-04-17 | Completed | Low | 3 | 3 | No changes requested; final approval received.