## Worksheet
Task ID | Task Name | Assigned To | Due Date | Priority | Status | Estimated Hours | Actual Hours | Progress (%)
T-001 | Design User Interface | Jane Doe | 2024-04-15 | High | In Progress | 8 | 6 | 75%
T-002 | Develop Backend API | John Smith | 2024-04-20 | Medium | Not Started | 15 | 0 | 0%
T-003 | Conduct User Testing | Lisa Chen | 2024-05-05 | High | Scheduled | 10 | 0 | 0%
T-004 | Prepare Documentation | Mike Brown | 2024-04-30 | Low | Completed | 5 | 5 | 100%
T-005 | Finalize Deployment Plan | Sarah Lee | 2024-05-10 | Medium | Not Started | 6 | 0 | 0%